## Burn Chart Data
# | Task Name | Planned Duration (Days) | Actual Duration (Days) | Planned Remaining | Actual Remaining
0 | Project Start | 0 | 0 | 190 | 190
1 | Sprint 0: Project Setup | 7 | 7 | 183 | 183
2 | Project Kickoff Meeting | 1 | 1 | 182 | 182
3 | Requirements Finalization | 2 | 3 | 180 | 179
4 | Dev Environment Setup | 2 | 2 | 178 | 177
5 | Database Schema Design | 2 | 2 | 176 | 175
6 | Sprint 1: Auth & User Mgmt | 14 | 15 | 162 | 160
7 | UI Design for Login Pages | 2 | 2 | 160 | 158
8 | Admin Login Module | 3 | 4 | 157 | 154
9 | Officer Login Module | 2 | 2 | 155 | 152
10 | Citizen Reg & Login | 3 | 3 | 152 | 149
11 | Role-Based Access Control | 2 | 2 | 150 | 147
12 | User Management Module | 2 | 2 | 148 | 145
13 | Sprint 2: Violation Detection | 14 | 14 | 134 | 131
14 | AI Model Integration Setup | 3 | 3 | 131 | 128
15 | License Plate OCR | 3 | 4 | 128 | 124
16 | Violation Detection Algorithm | 4 | 3 | 124 | 121
17 | Manual Violation Recording | 2 | 2 | 122 | 119
18 | Evidence Capture & Storage | 2 | 2 | 120 | 117
19 | Sprint 3: E-Challan Mgmt | 14 | 13 | 106 | 104
20 | RTO Database Integration | 3 | 3 | 103 | 101
21 | Vehicle Verification Module | 2 | 2 | 101 | 99
22 | E-Challan Generation Engine | 3 | 2 | 98 | 97
23 | Challan PDF Generation | 2 | 2 | 96 | 95
24 | SMS/Email Notification | 2 | 2 | 94 | 93
25 | Challan Status Management | 2 | 2 | 92 | 91
26 | Sprint 4: Payment Integration | 14 | 15 | 78 | 76
27 | Payment Gateway API | 3 | 3 | 75 | 73
28 | Online Payment Module | 3 | 4 | 72 | 69
29 | Payment Verification | 2 | 2 | 70 | 67
30 | Receipt Generation System | 2 | 2 | 68 | 65
31 | Refund Processing Module | 2 | 2 | 66 | 63
32 | Payment History & Reports | 2 | 2 | 64 | 61
33 | Sprint 5: Dashboards | 14 | 14 | 50 | 47
34 | Admin Dashboard UI | 2 | 2 | 48 | 45
35 | Real-Time Analytics | 3 | 3 | 45 | 42
36 | Officer Dashboard Dev | 3 | 3 | 42 | 39
37 | Citizen Portal Dev | 3 | 3 | 39 | 36
38 | Report Generation Module | 2 | 2 | 37 | 34
39 | Mobile App Development | 1 | 1 | 36 | 33
40 | Sprint 6: Testing & Deploy | 14 | 13 | 22 | 20
41 | Unit Testing | 3 | 3 | 19 | 17
42 | Integration Testing | 3 | 2 | 16 | 15
43 | User Acceptance Testing | 3 | 3 | 13 | 12
44 | Bug Fixes & Optimization | 2 | 2 | 11 | 10
45 | Production Deployment | 2 | 2 | 9 | 8
46 | Documentation & Training | 1 | 1 | 8 | 7
47 | Buffer & Final Review | 4 | 4 | 4 | 3
48 | System Performance Review | 1 | 1 | 3 | 2
49 | Stakeholder Demo | 1 | 1 | 2 | 1
50 | Final Documentation | 1 | 1 | 1 | 0
51 | Project Closure | 1 | 1 | 0 | 0

## Burn Chart
FL-TMS 2.0 – Project Burn Chart